## Slide 1
NWE Day-Ahead Project
Status Update 2nd IG meeting
NRA meeting October 26th
Joint Presentation from TSOs and PXs from the NWE Region

## Slide 2: Introduction
ACER presented in September 2011 a roadmap to request TSOs and PXs to deliver a single European price coupling by 2014
First step is to deliver NWE (CWE, Nordic, GB) by the end of 2012
These slides intend to provide a clear status to NRAs on the progress of the NWE day-ahead price coupling project
They also contain the first answers to the questions raised by regulators on 6 Oct. 2011

## Slide 3: Introduction
NWE TSOs and PXs recognise the importance of NWE as a pragmatic implementation project
All TSOs and PXs in NWE have already taken the commitment to replace ITVC in June 2012 when ITVC was launched in November 2010
NWE has a central role due to geography and advanced development
The time schedules are challenging and the NWE TSOs and NWE PXs, as well as the regulators, need to focus to have a smooth and efficient achievement of the NWE price coupling

## Slide 4: Content
European development and scope for the NWE project
NWE project – Common TSO – PX project
Projects steps and timeline
Cost issues
Algorithm requirements
Governance arrangements

## Slide 5: Towards a common European power market
The Nordic market – 2000
  Including Estonia 2010 (and full Baltic prel. end 2012)
Central West Europe – 2010
ITVC – 2011
  Including embedded solution for BritNed cable to UK via APX and Price Coupling on SwePol via NPS
Chart: 
| Norden | CWE | NWE tillegg | Europe tillegg
Salg | 400 | 2000 | 200 | 900
2200 TWh

## Slide 6: Towards a common European power market
Chart: 
| Norden | CWE | NWE tillegg | Europe tillegg
Salg | 400 | 1400 | 500 | 900
2300 TWh
The Nordic market – 2000
  Including Estonia 2010 (and full Baltic prel. end 2012)
Central West Europe – 2010
ITVC – 2011
Including embedded solution for BritNed cable to UK via APX and Price Coupling on SwePol via NPS
North West Europe – 2012

## Slide 7: Towards a common European power market
The Nordic market – 2000
Central West Europe – 2010
ITVC – 2011
North West Europe – 2012
European solution – 2013 & 2014
Chart: 
| Norden | CWE | NWE tillegg | Europe tillegg
Salg | 400 | 1400 | 500 | 900
3200 TWh

## Slide 8: NWE – the first phase proposed by ACER for Europe
13 TSOs
NWE TSOs have signed agreement with CASC – TSO project manager
  TSO Project Manager – Corne Meeuwis – CASC
  100 % dedicated Project Conveners (TF leaders) hired by CASC – secure focus, deliverables and progress
3 PXs
Common organisation and project structure to be decided 28th October

## Slide 9: NWE - Common project between the NWE TSOs and PXs
Good progress made between NWE PXs and TSOs:
Agreement that PCR concept with a set of TSO requirements is the basis for the coordinated matching function
Governance and cost management to cover design and implementation phase in All Party Cooperation Agreement (APCA)
  Aim to sign as soon as possible to keep the momentum in the project
Governance contract for operational phase to be developed as project deliverable, based on principles agreed in APCA

## Slide 10: NWE - Common project between the NWE TSOs and PXs (cont).
Joint technical meetings are already taking place with the aim of clarifying and describe the technical design and business processes
  Description of system architecture, system components and system interfaces
  Description of business processes in all scenario’s (normal, fallback,…) (including pre-coupling and post-coupling processes)
  Industrialise and test the systems
  Train staff and market parties

## Slide 11: Overview Project Steps
Initiation agreed while APCA is finalized and signed
  Project kick-off: setup project structure
  PXs agree to continue PCR – NWE work pending APCA
Design Phase
  Impact analysis and change specifications, cost and cost recovery, algorithm requirements, algorithm prototype, governance for the operations phase, approvals
3. Implementation Phase
  Build/test/commission systems, prepare operations phase, communication to stakeholders
Operational phase
  Daily operations and maintenance

## Slide 12: NWE – high level timeline
2011
2012
Oct
Dec
Feb
Apr
Jun
Aug
Oct
Dec
Initiation
Design phase
Implementation phase
Go-Live
Preparation
PXs are considering options if need to accelerate delivery
  Request supplier to propose options to meet fixed NWE deadline
  Postpone functionality not considered critical for NWE launch, e.g. use manual interfaces
  Postpone testing of business processes not critical for NWE
  If necessary, a similar approach could be taken with the Algorithm

## Slide 13: Cost recovery issues
PXs and TSOs need transparency towards themselves and regulators on their budgets and incurred costs.
The NWE is driven by the principle of cost efficiency and using as much as possible existing infrastructure.
Moreover, subject to the above, PXs and TSOs have reached the following agreements:
  Agreement that NWE share of PCR costs for the design phase will be 60 %
  Budget for the design phase and (more preliminary) implementation phase will be presented in October
  Based on the budget, NWE cost recovery for the design phase will be organized centrally and paid by the NWE TSOs
  Firm budget for the implementation phase will be presented by the PXs as soon as possible (post design completion)
  NWE cost recovery for the implementation and operational phases will be decided taking into account e.g. regulatory requirements
  The NWE APCA to be signed will implement these principles

## Slide 14: Algorithm Transparency and Readiness
The main elements/components of the PCR starting point algorithm (which is the COSMOS algorithm in production in CWE) are already publicly available at http://static.epexspot.com/document/9606/COSMOS_public_description.pdf
Beyond this description, PXs and TSOs support that there should be suitable transparency at least as good as that currently provided across the different markets today

## Slide 15: PCR Assessment – NWE report delivered to ENTSO-E
ACER requested ENTSO-E to assess COSMOS as a PCR starting point by October 2011
NWE TSOs have checked how far their algorithm requirements are met and what development work is needed to create the prototype, especially in the NWE region
Assessment shows, in general
  majority of the requirements is in operation or has already been developed and tested in CWE context
  however, all these requirements shall be tested in NWE context
  a couple of requirements need further development and investigation before implementation, because they have not been addressed before

## Slide 16: Algorithm requirements – input & output
Input:
  local order books submitted by PXs; PXs shall determine format and content
  network constraints provided for by the TSOs; TSOs shall determine format and content
Output:
  Market Clearing Price (MCP) for each bidding area for each hour,
  set of accepted and rejected orders
  net surplus/deficit (or export/import position) for each bidding area
  shadow price of each constraint (for example flow based constraints)
  slack value on each constraint

## Slide 17: Algorithm requirements – network & welfare optimisation
Network constraints
The ability to update the grid model, the constraints' format, and ability to change the number of constraints and price areas in their networks
The algorithm shall be able to handle the network constraint types and formats (Flow-Based or ATC approach or hybrid FBA/ATC)
Social welfare optimisation
The optimisation goal is to maximise social welfare. The social welfare shall be summed over all bidding areas and hours and bid types, respectively.

## Slide 18: Algorithm requirements - TSOs
Right of audit of the algorithm as regards capacity allocation on:
  costs
  algorithm (mathematical description)
  all results of the capacity allocated by market coupling
  IT systems
  procedures and business processes
Access to simulation tool and all historical market data to verify that capacity allocation is allocated according to requirements
  Trigger further development of algorithm – new capacity allocation requirements to be implemented also after go live

## Slide 19: General algorithm requirements
    Costs e.g. losses
    Ramping constraints
    Minimum flows on DC lines
Reliability
    Fairness
    Reproducibility
    Simplicity
    Currency
    Price boundaries
    Negative prices
    Calculation time/cut-off
    Transparency
    Extendibility
    Winter and Summer Time

## Slide 20: NWE High Level Governance
NWE TSOs and PXs recognise the importance of NWE as a pragmatic implementation project also in terms of governance
  the project governance will be light and pragmatic
  the Governance Guideline driven by the EC will provide the EU-wide governance solution, hence initial arrangements might have to be adapted at a later stage
  The TSO cooperation in NWE is extended to other TSOs in Europe through ENTSO-E
  The PXs in NWE are using the PCR solution being developed together with other European PXs

## Slide 21: Governance Arrangements
Monthly common PX-TSO SC meetings to govern the NWE project
A joint SC between PXs and TSOs for the operational phase to be discussed
In terms of PCR/NWE algorithm and systems delivered by the PXs, there is common understanding that TSOs are involved in the developments of the total solution, and their control is limited to all aspects of efficient allocation of capacities and corresponding requirements
Direct regulatory oversight of the market coupling arrangements is supported by all parties
Reuse most of existing regional subsidiary agreements (including shipping and cross-PX clearing)

## Slide 22: Governance Arrangements (cont)
During the Project Phase, set up all- party Agreement before launch that should cover amongst others:
Transparency
Judging and maintaining the efficiency and adequacy of the solution, including a proper allocation service quality level during the operations
Effective decision making
Transition to the pan-European solution and neutrality to new entrants
That energy regulators should directly regulate the energy market/matching rules (PXs) under the relevant regulations by usage of suitable tools

## Slide 23
The first phase is the price coupling in North West Europe