## Slide 1
34rd meeting of the
Implementation Group
on Congestion Management (IG)
Presentation of the CEE TSOs
20 February 2014
Vienna

## Slide 2
Table of contents
  Recent Developments
  Status report CEE TSOs
  II. CEE FB MC Project Development and Implementation
  II.1 Status report
  II.2 Project structure, project management
II.3 Cooperation CWE/NWE and CEE
    II.4. Roadmap elaboration
    II.5. Further steps

## Slide 3
2014 – 2 – 20 CEE TSOs - IG meeting Vienna
I. Recent Developments
Status Report of CEE TSOs (1/3)
Governance Workstream:
CEE TSOs have taken note of the final version of the MoU and the signature process started by the Lead Regulator ECA
CEE TSOs have approved on 31 January to start immediately with the initiation of the NWCE MC project by setting up the project structure from the TSO-side (JSC and JWG MC) and invite CEE PXs to do the same
  Call for nomination of TSO members and potential chairpersons have been sent out
  PXs have been invited to do the same
  CEE TSOs nominated members and voted on a chairperson
  FP will organise the first JSC meeting as soon as PX members have been communicated to FP

## Slide 4
2014 – 2 – 20 CEE TSOs - IG meeting Vienna
I. Recent Developments
Status Report of CEE TSOs (2/3)
Technical Workstream:
CEE TSOs achieved consensus on how to continue the work on the two options in order to take better into account unscheduled flows in the FB methodology
Security Oriented Option (SOO)
  Based on today´s bidding zones, considering/mitigating the influence of loop flows - limitation (cap) of exchange schedules between DE and AT by redispatching/countertrading measures, considering this limitation in the FB capacity calculation mechanism.
  Progress was achieved on the SOO. The CEE TSO HLM stated that the preparatory step was finalized and step 1 can be started.
  Finalisation of dBFRM assessment was achieved, WG FBA started with calculation for 120 timestamps of the year 2013
  Final results for step 1 are expected for end of July 2014

## Slide 5
2014 – 2 – 20 CEE TSOs - IG meeting Vienna
I. Recent Developments
Status Report of CEE TSOs (3/3)
Technical Workstream:
Financial Compensation Oriented Option (FCOO)
  Based on today´s bidding zones, considering the influence of loop flows – focusing on social welfare differences between situations with/ without prioritized schedules for DE-AT, define a compensation mechanism.
  Out of several sub-options, the CEE TSO HLM agreed on selecting sub-option 1A (social-welfare-oriented, no DE-AT market splitting) for further elaboration.
  Letter to PCR will be sent in order to get support for the simulations
  Both options (COO Step 2) and FCOO need a market simulation tool and a market coupling simulation tool: CEE TSOs are exploring the market and giving recommendations to the WGs. Market simulation for bidding zone will be assessed if it is available timely.

## Slide 6
2014 – 2 – 20 CEE TSOs - IG meeting Vienna
II. CEE FB MC Project Development and Implementation
II.1. Status Report
CEE TSOs have started to initiate the project structure – see status report under agenda point I.
ToRs for JSC and JWG MC received from PXs commented and sent back for approval
Assessment of PCR algorithm
  Negotiations on NDA/CD with PCR parties still ongoing
  In the mean time PCR has published information on Euphemia algorithm, CEE TSOs are assessing the public information on Euphemia
  CEE TSOs are looking for a meeting of experts with PCR in order to assess whether this public information is sufficient to go on
  Regional NDA for TSOs and PXs for the NWCE FB project has priority

## Slide 7
2014 – 2 – 20 CEE TSOs - IG meeting Vienna
II. CEE FB MC Project Development and Implementation
II.2. Project structure, project management
JSC
CEE TSO HLM
WG CA
WG Scheduling
JWG MC
STF Reg /Com
STF Legal
CEEE Forum (Ministries, EC, ACER, TSOs, PXs, NRAS, Market Parties)
IG Meeting (NRAs, EC, ACER, TSOs, PXs)
PMO
TF Algorithm & FB Validation
TF Shipping
TF Operational Procedures
TF Testing
WG FBA
PXs MM
PX WG MC
governance
communication exchange

## Slide 8
2014 – 2 – 20 CEE TSOs - IG meeting Vienna
II. CEE FB MC Project Development and Implementation
II.2. Project structure, project management – ToRs JSC
Main decision making body
  Binding approval of design concepts, agreements, reports and other documents which are elaborated by respective working groups;
  Delegation of tasks and engagement of external support (e.g. the Project Manager (PMO));
  Changes to the Project and the Project roadmap;
  Joint external communication on the Project including quality and quantity of information provided on the Project and timing of the delivery of such information to other stakeholders/ the public;
  Establishment of Task Forces and Supportive Task Forces, setting and amendment of terms of reference for Joint Working Group Market Coupling
  Budgeting and costs approval ,
  Presentation of costs to relevant decision bodies including request for relevant costs comfort.
  Decision on and definition of the modalities of the involvement of other relevant stakeholders. Supportive Task Forces work on ad-hoc basis in order to support different workstreams.
Each partner one vote – unanimous decision
Each TSO, PX one member + substitute, guest can be invited without voting power
Co-Chairs from both TSOs – PXs – elected for a term of 12 month
JSC may engage a PMO

## Slide 9
2014 – 2 – 20 CEE TSOs - IG meeting Vienna
II. CEE FB MC Project Development and Implementation
II.2. Project structure, project management – ToRs JWG MC (1/2)
Main tasks (to be defined by JSC)
  Algorithm and FB validation
  Development of Market Design
  Development and implementation of shipping concept
  Preparation and performance of testing
  Continuous budget planning and monitoring (as long as PMO has not been established)
    Supervision of the budget planning and monitoring after PMO has been established
  Development of cost-sharing and cost-recovery principles for implementation and operation phase
    Decision on what costs may be shared (Costs of PMO, time of the Chairmen, Conveners and Co-Conveners etc.)
  Provision of drafts for the necessary contracts and organization of signing procedures
  Press release management
  Identification of required regulatory approvals and their timing
  Organization of timely regulatory approval processes
  Monitoring of and reporting on implementation
  Preparation and performance of PMO selection procedure and recommendation of (selected) PMO to JSC

## Slide 10
2014 – 2 – 20 CEE TSOs - IG meeting Vienna
II. CEE FB MC Project Development and Implementation
II.2. Project structure, project management – ToRs JWG MC (2/2)
Deliverables
  Drafting and negotiation of the FPA for the design phase ;
  Unambiguous and measurable acceptance criteria for Go-Live;
  Penalties/indemnity clauses, liability;
  Development of cost sharing principles etc.;
  Budget planning for the Project;
  Drafting and negotiation of the NDAs necessary for the design phase;
  Description of individual TFs responsibilities and deliverables
Supported by Task Forces (TF) and ad-hoc groups (sTF)
Each partner one vote – unanimous decision
Each TSO, PX one member + substitute, guest can be invited without voting power
Co-Chairs from both TSO – PXs

## Slide 11
2014 – 2 – 20 CEE TSOs - IG meeting Vienna
II. CEE FB MC Project Development and Implementation
II.3. Cooperation CWE/NWE and CEE
NWE TSOs have been busy in the past due to NWE MC project
NWE structures may change with the finalisation of the project
Some TSOs and PXs are involved in other regions and can bring in their experiences and knowledge (without disclosing protected information)
CEE TSOs recommend to start with the project on regional level and address NWE TSOs on issues where we need their information/involvement
WG RMDT identified indicative issues where we might need cooperation of NWE TSOs
  High priority issues related to the design phase: Bilateral energy exchange calculations; Operational procedures connected to the coupling phase
  Medium priority: PCR algorithm assessment; Testing
  Lower priority: Cross-regional operational agreements
  Harmonisation with CWE FB – after CEE have common understanding of FB methodology in CEE
There might be the need discuss with NWE resources and timing as there are other regions (SWE, CSE, NBI) are heading for a coupling at the same time
Highly depending on the final Roadmap to be amended by JSC asap

## Slide 12
2014 – 2 – 20 CEE TSOs - IG meeting Vienna
II. CEE FB MC Project Development and Implementation
II.4. Roadmap elaboration (1/2)
 | 2014 |  |  |  |  |  | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  |  |  |  |  |  | 
 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7
MoU preparation and signing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
NDA preparation and signing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Creation of CEE project structure |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Budget planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Cost Sharing principles |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Framework Project Agreement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Validation of MC Algorithm |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
PCR - involvement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
CEE/CWE FB harmonization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
CEE FB capacity calculation mechanism |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Cross-border clearing and settlement process |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Congestion income distribution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Other postcoupling processes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Fallback procedures |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Operational contracts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
FB MC testing - Internal |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
FB MC testing -External |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
CEE + NWE testing - Acceptance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Evaluation and consultation of FB MC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Initiation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Go Live |  | 
Design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Implementation (& Testing/Approval) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Final Approval for Go Live |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 13
2014 – 2 – 20 CEE TSOs - IG meeting Vienna
II. CEE FB MC Project Development and Implementation
II.4. Roadmap elaboration (2/2)
CEE TSOs have drafted the Roadmap based on the Project Initiation Document elaborated between CEE TSOs and PXs, but without involvement of NWE
Current Roadmap sees a period of 27 month after MoU signature for the finalisation of the project
Regulators have asked to revise the roadmap
CEE TSOs have made the decision to hand this over to the JSC/JWG MC as involvement of PXs is needed for the revision

## Slide 14
2014 – 2 – 20 CEE TSOs - IG meeting Vienna
II. CEE FB MC Project Development and Implementation
II.5. Further steps
Agreement with PX’s on ToRs of JSC and JWG MC
Organisation of first JSC meeting by FP
JSC has then to take the next steps according ToRs