## Slide 1: PCR Status report
AESAG, September 5 2012
Supported by:

## Slide 2
PCR agreements status
Signed by six PCR PXs
Questions received answered to AESAG participants
PCR open to continue receiving and answering questions from AESAG participants regarding the agreements
Discussions on going with other PXs to incorporate them to the PCR process
PCR development suppliers main contracts status
Systems (PMB) development contract signed.
  Maintenance contract in final discussion
Price Coupling algorithm (Euphemia) development contract signed.
  Maintenance contract under discussion
Communications infrastructure installation and maintenance contracts signed.

## Slide 3
PCR development status – price coupling algorithm (Euphemia)
Industrialization work on going
    Several releases already received from the provider
Extensive testing of the industrialized version on going
  Functional tests
  Historical batches tests (2011)
  Stress batch tests (historical data modified to stress the algorithm)
  Some functionality to be included in future releases
Tests linked to the PCR Matcher-Broker (PMB) and special case handling (decoupling, curtailment, etc. ) ready to start
If new requirements appear they will be treated under change control
  Impact to be evaluated

## Slide 4
PCR development status – Support Information System - PMB (PCR Matcher and Broker)
  Several releases of the PMB system received from the provider and under testing
  Project Manager and Test coordinator structure operating
  Test team for PMB, formed by Test Leaders and supporters from each PCR PX together with Test Coordinator operating
    Test plans and scenarios finished
    Several training workshop for testers already took place
  Local testing systems installed in each PX locations.
  Parallel testing running on the different local installations
  Integration tests between PCR PXs scheduled for mid-October
  Extended tests (Post system acceptance) scheduled for January
  Clarification of a few TSO related requirements still not completely finalized yet
    Impact to be evaluated under change control when known
    Some functionality to be added in future releases after first regional implementations(s) based on the PCR Price Coupling solution

## Slide 5
PCR development status. Operational Manual
  Main Principles established in the PCR cooperation agreement, in line with the draft Governance Guideline
  Details to be developed starting from, and adapting, primarily the CWE Operational Manual
  PCR Normal procedures soon ready for internal approval
  PCR Backup procedures in development stage
  PCR Exceptional procedures prepared
  PCR Fall-back procedures under development
  PCR Checklist (actions form all procedures) under development
  Coordination with Regional projects procedures (timing, etc…)

## Slide 6
Regional implementations of PCR (I)
PCR doesn´t cover any pre- or post- coupling steps (e.g. shipping or clearing) and what specific solutions for exceptional situations are utilized on each border, or groups of borders. It is up to bilateral (or multilateral) decisions of relevant Parties;
In line with ACER road map
NWE
  See detailed complementary presentation by NWE PXs and TSOs

## Slide 7
Regional implementation of PCR (II)
MIBEL-France (Pre coupling, post coupling and exceptional situations)
  Under the SWE Regional Implementation Group coordination
  Limited to pre coupling, post coupling and exceptional situations processes
  Cooperation agreement finished and under signature process
  Working groups formed to follow the development of the different components necessary
  Existing procedures respected as much as possible
  Coordination with other Regions very important for the PX and the TSO involved also in NWE
  The PXs are developing the interface between the trading system and PMB (compress bid preparation, portfolio allocation, validations, etc…)

## Slide 8
Regional implementation of PCR (III)
CSE
  CSE PXs evaluating their participation on PCR
  PCR fully consistent with the coupling already in place between Italy and Slovenia. Italy will take part in name of both to the testing phase starting in October, as for the system operation.
  First discussions concerning the structuring of a pre-post coupling process involving TSOs and PXs also on the French border
  Start up of a working group for implementation of the market coupling for day ahead and intraday markets between the relevant PX and TSOs on the Italian borders

## Slide 9
Regional implementation of PCR (IV)
CEE-NWE
  Austria, Czech, Germany, Hungary, Poland, Slovakia and Slovenia involved in the project of MC FBA CEE-NWE
  MoU including Implementation roadmap is being prepared
  Support of NRAs and TSOs: MC to be based on PCR.
  CEE PXs to choose between becoming full PCR members or being serviced by one of the full PCR members.
  Coordination with NWE and PCR members is inevitable for the PXs and the TSOs involved in CEE for further implementation
  Additional requirements of CEE TSOs to PCR algorithm need to be clarified and discussed, which can prolong implementation
  First discussions concerning the structuring of a pre-post coupling process involving TSOs and PXs
  Next steps – signature of MoU and start work on the design and Framework Project Agreement.