## Slide 1: PCR Status Date: 5 December 2012

## Slide 2: Content
Achievements
Revised planning outlook
Reasons for delays
Remaining risks

## Slide 3: Achievements
Algorithm release 3 delivered and in test
  Release 4 foreseen for last bug fixing on release 3
PCR Matcher Broker (PBM) software Release 2 getting stable
  Release 3 expected for some additional plugins
Procedures:
  Draft versions available – some issues identified on timings
  Alignment discussions between PCR and NWE on timings are currently ongoing
Testing infrastructure installed:
  Algorithm integrated in PBM
  PMB being integrated in local trading systems
  Connectivity between different PMBs at different PXs established
  Sanity tests are starting ( check of file formats and exchange etc…) as preparation for the 5 PX integration tests
  Test scenario’s are prepared

## Slide 4: Current Planning Outlook
Base case planning:
  Handover of PMB release 2.X.X + Algorithm release 4 by end of April 2013
  Handover of PMB release 3 + Algorithm release 4 by end of May 2013
  This base case planning includes the change request for flow calculation but not the change request for LT nomination into ramping constraints
Budget consequences are currently under investigation

## Slide 5: Reasons for delays
  Difficulties to agree on final specs
  Several requests for changes from PXs and TSOs
  Software quality issues in first releases of algorithm and PMB leading to delays in the tests and extra bug fixing work
  Difficulties installing local test environments

## Slide 6: Remaining Risks
Unexpected testing issues in algorithm release 3
Unexpected testing issues in the PMB releases 2.X.X and 3
Change of currently specified flow calculation method after simulations
Overall delay ( increase in the variable project costs)

## Slide 7: Membership and other requests
OTE requested full membership:
  Preparation started in PCR
  Discussion to start between PCR and OTE
LAGIE, greek market operator, signed confidentiality declaration for associate membership
Other associate members also requesting information on cost reinvoicing
CEE TSOs requested for assessment about algorithm compatibility with CEE
 Important not to disturb current PCR progress