## Slide 1
NWE Day-Ahead Price Coupling
IG meeting May 9th 2012
Copenhagen
Joint Presentation from TSOs and PXs from the NWE Region

## Slide 2: Content
Status on the APCA/ Comfort letter
Joint Project Organisation
Regulator Questions from last IG meeting

## Slide 3: All Party Cooperation Agreement (APCA)
The APCA for design and implementation is a framework agreement, with annexes setting out e.g. governing principles, budget, cost sharing, plan, decision making process and high level principles for operation of market coupling
The agreement is negotiated by the NWE PXs and TSOs, and is expected to be ready for signature before Florence forum (22. and 23. May)
TSOs have stated need for comfort that NWE related costs will be accepted by the NRAs prior to signing or entry into force of the APCA

## Slide 4: The Comfort Letter
The purpose of the comfort letter is to deliver sufficient information to enable the lead NRAs of the NWE project to facilitate issuing of a comfort letter, and thereby to facilitate signing of the cooperation agreement between the TSOs and PXs in May, in order to safeguard expedient and timely delivery of the project.
Information provided in the letter is, governance and cooperation principles, cost sharing and cost recovery principles, budget, algorithm requirements and high level price coupling governance principles

## Slide 5: Joint Project Organisation (1/2)
Joint PMO
(Consultant: E-Bridge )
NWE JSC
Technical
WG
Corne Meeuwis
Legal, Regulatory
and Market WG
Tjitske Kramer
Procedures TF
Testing TF
Capacity TF
Local
Sub-Projects
Shipping TF
Regulatory TF
Shipping Financial TF
TSO-only
Sub-Project
Reporting
External
Communication
& Markets TF
Legal &
Contracts TF
PX-only
Sub-Project
ITVC Shipping
Sub task
GB Shipping
Sub task
Algorithm TF

## Slide 6: Joint Project Organisation (2/2)
NWE JSC (TSOs and PXs)
This function is acting as a Board, making major decisions and safeguarding timely completion of the NWE project.
Working Groups (chairs: Corné Meeuwis and Tjitske Kramer)
2 main WGs, one technical (Corné) and one legal and regulatory (Tjitske). The WG chairs are with the support of the PMO, responsible for progress and are reporting to JSC.
PMO (E-Bridge)
This function is facilitating the work in the joint project, acting as “secretary general”.
Task Forces
Representation of all parties, or 3-4 specialists and reading members (1 per party).

## Slide 7: NRA questions from last IG meeting
Question:
NRAs request more detailed information on budget. Preferably, this should be sent together with TSOs’/PXs’ request for regulatory approval of sharing arrangements and validation of common and local costs
Answer:
A comfort letter is prepared, and are ready to be forwarded, with the required information on the budget.

## Slide 8: Answer to NRA Budget request 1/2
Preliminary budgets for design and implementation comprise:
Combined NWE PX costs of €10.3m
  €3.3m (60%) of PCR Common Costs (commonly procured services: project manager, taskforce leaders, algorithm and system development)
  €7m of local costs (support to PCR/NWE project plus PX-specific changes)
NWE Common Costs of €0.8m, excluding shipping implementation costs (project office, taskforce leaders)
  Project Management Office (PMO) costs amount €0.37m
  WG leaders are paid as PXs-only respectively TSOs-only, and therefore not part of the common costs.
The budgets assume a go-live at the end of December of NWE Market Coupling based on the PCR/PMB solution. The budgets will be finalised as part of the APCA completion process during early May. Any change to this plan and possible budget changes are subject to JSC approval.

## Slide 9: Answer to NRA Budget request 2/2
In this overview, the shading indicates:

## Slide 10: NRA questions from last IG meeting
Questions:
NRAs request to provide a proposal for cost sharing between NWE and non-NWE countries
Answer:
The NWE TSOs and PXs will, provided regulatory approval, pay their share (60 %) of the PCR costs. The NWE parties will also pay NWE related cost. The non-NWE TSOs and PXs should pay 40 % of the PCR costs and all non- NWE related costs.
The APCA facilitates geographical extension of the price coupling, new PXs and TSOs shall pay for regional adaptation provided they have special needs.

## Slide 11: NRA questions from last IG meeting
Questions:
NRAs request a clear proposal on high level flexible high-level interim governance arrangements for the NWE project.
Answer:
The APCA includes an annex (NR. 6: Price Coupling governance principles) with the high level governance arrangements. The governance arrangements are also described in the comfort letter.
The Parties acknowledge that currently Governance Guidelines are being drafted and negotiated with the European authorities. Such legislation under development may affect the cooperation under this NWE APCA, and this is reflected in the APCA. The parties do not see any particular challenges in this respect.

## Slide 12: Answer to NRA request for proposal on governance arrangements (APCA Annex Nr. 6)
Capacity allocation is a TSO responsibility, pursuant to the provisions of Directive 2009/72/EC of 13 July 2009 concerning common rules for the internal market in electricity, and of Regulation (EC) No 714/2009 of 13 July 2009 on conditions for access to the network for cross-border exchanges in electricity.
PXs are responsible for operating their respective markets (including price formation), under various contractual and/or regulatory arrangements.
The nature of capacity allocation is that of a monopolistic function, the TSOs are regulated entities, and therefore the TSOs need at all times to be in a position to have sufficient comfort on compliance, in particular on the cooperation between the PXs (of the NWE Region or broader in PCR as the case may be), to achieve the Enduring Solution with the following criteria (the “Compliance”):
1. Competition law compliance
2. Geographical expansion of Price Coupling
3. PCR Solution for NWE
4. Cost efficiency
5. PXs’ role of operators