## Slide 1
Enagás IT roadmap
CAM & CMP
19 July 2013

## Slide 2
Index
  CAM IT roadmap
  CMP IT roadmap

## Slide 3
2013
2014
2015
Enagás CAM IT roadmap
CAM Implementation (auctions & products)
Jul/13
Kick-off IT specifications (CAM)
CAM impact on billing
Oct/14
Release production environment (CAM impact on billing)
Jul/13
Kick-off IT specifications (CAM impact on billing)
Sep/13
Finalisation of IT specifications (CAM impact on billing)
Main milestones
Release environment
Start of auctions
Annual yearly capacity auctions
Annual quarterly capacity auctions
Rolling monthly capacity auctions
Rolling day ahead capacity auctions
Within-day capacity auctions
1st Monday March 2014
1st Monday June 2014
3rd Monday Sep 2014
30th Sep 2015
1st Monday March 2015
1st Monday June 2015
Nov/15
CAM NC binding implementation
Jul/13
PRISMA decision
Mar/14
CAM NC early implementation for S-GRI
Nov 2015
Nominations (nominations & matching process agreed within the S-GRI TSOs )
Sep/13
Kick-off IT specifications (Nominations)
Sep/14
Finalisation of IT specifications (Nominations)
Nov/15
Release production environment (Nominations)
Sep/13
Finalisation of IT specifications (CAM)
Sep/14
Release production environment (CAM)
Interim period

## Slide 4
Index
  CAM IT roadmap
  CMP IT roadmap

## Slide 5
2013
2014
Enagás CMP IT roadmap - Surrender
CMP Implementation (impact on CAM - auctions & products)
Jul/13
Kick-off IT specifications
CMP impact on billing
Jul/13
Kick-off IT specifications
Sep/13
Finalisation of IT specifications
Main milestones
Release environment
Surrender
1st Monday March 2014
Oct/13
CMP binding implementation
Jul/16
ST UIOLI binding implementation
2015
2016
Surrender will be implemented as of 1 October 2013. This capacity will be added on the top of the available capacities.
This procedure will be automatically offered through auctions as the same time as the CAM NC implementation. Thus, the IT roadmap will be the same as CAM.
Surrender IT roadmap is based on the CMP roadmap presented by TSOs, if the products offered through surrender vary the roadmap should be accordingly amendment
Sep/14
Release production environment
Sep/13
Finalisation of IT specifications
Oct/14
Release production environment (surrender impact on billing)
Mar/14
CAM NC early implementation for S-GRI
Surrender will be offered on FCFS basis after the available capacity
Start of auctions
3rd Monday Sep 2014
1st Monday Jun 2014

## Slide 6
2013
2014
Enagás CMP IT roadmap – LT UIOLI
CMP Implementation (impact on CAM - auctions & products)
Jul/13
Kick-off IT specifications (LT UIOLI)
CMP impact on billing
Jul/13
Kick-off IT specifications LT UIOLI)
Oct/14
Finalisation of IT specifications (LT UIOLI)
Main milestones
Release environment
Included in auctions
LT UIOLI
Oct/13
CMP binding implementation
Jul/16
ST UIOLI binding implementation
2015
2016
1st Monday June 2015
LT UIOLI IT roadmap is based on the CMP roadmap jointly developed by TSOs. If the details of the LT UIOLI approved by CNE vary from the CMP roadmap developed by TSOs, this IT roadmap might change.
Apr/15
Query to identify the UIOLI LT information
1st Monday March 2015
Mar/15
Release production environment (LT UIOLI)
Mar/14
Finalisation of IT specifications (LT UIOLI)
Oct/15
Release production environment (LT UIOLI)
As of October 2013 until March 2015, the LT UIOLI procedure to be applied is the one included in RD 949/2001

## Slide 7
2013
2014
Enagás CMP IT roadmap – ST UIOLI
CMP Implementation (impact on CAM - auctions & products), CMP impact on billing, Nominations
Jun/14
Kick-off IT specifications (ST UIOLI)
Jun/15
Finalisation of IT specifications (ST UIOLI)
Main milestones
Release environment
Binding implementation
ST UIOLI
Oct/13
CMP binding implementation
Jul/16
ST UIOLI binding implementation
2015
2016
30th June 2016
Jun/16
Release production environment (ST UIOLI)
The deadlines included in this roadmap are based on estimations made exclusively by Enagás. It is worth noting that discussions with the adjacent TSOs have not yet started so the roadmap is subject to modifications.

## Slide 8
2013
2014
Enagás CMP IT roadmap – OSBB
CMP Implementation (impact on CAM - auctions & products), CMP impact on billing, Nominations
Main milestones
Release environment
Binding implementation
OSBB
Oct/13
CMP binding implementation
Jul/16
ST UIOLI binding implementation
2015
2016
The OSBB procedure proposed by CNE varies significantly from the procedure included by the TSOs in the CMP roadmap.
Besides, in order to implement the OSBB procedure proposed by CNE, a common platform is needed. Up to now Prisma does not offer this functionality.
Further details and analysis is needed before developing an IT roadmap

## Slide 9
Gracias por su atención.